## Sheet1
Date | Week 1 | [5 empty] | Week 2 | [5 empty] | Week 3 | [5 empty] | Week 4 | [5 empty] | Week 5 | [5 empty] | Week 6 | [5 empty] | Week 7 | [5 empty] | Week 8 (Wed) |  |  | Week 9 (Wed) |  |  | Week Easter | [5 empty] | Week 10 | [5 empty] | Progress
Sessions | Morning |  |  | Afternoon |  |  | Morning |  |  | Afternoon |  |  | Morning |  |  | Afternoon |  |  | Morning |  |  | Afternoon |  |  | Morning |  |  | Afternoon |  |  | Morning |  |  | Afternoon |  |  | Morning |  |  | Afternoon |  |  | Afternoon |  |  | Afternoon |  |  | 2017-04-05 |  |  | 2017-04-26 |  |  | Morning |  |  | Afternoon
Time | 10-11 | 11-12 | 12-13 | 14-15 | 15-16 | 16-17 | 10-11 | 11-12 | 12-13 | 14-15 | 15-16 | 16-17 | 10-11 | 11-12 | 12-13 | 14-15 | 15-16 | 16-17 | 10-11 | 11-12 | 12-13 | 14-15 | 15-16 | 16-17 | 10-11 | 11-12 | 12-13 | 14-15 | 15-16 | 16-17 | 10-11 | 11-12 | 12-13 | 14-15 | 15-16 | 16-17 | 10-11 | 11-12 | 12-13 | 14-15 | 15-16 | 16-17 | 14-15 | 15-16 | 16-17 | 14-15 | 15-16 | 16-17 | 14-15 | 15-16 | 16-17 | 14-15 | 15-16 | 16-17 | 10-11 | 11-12 | 12-13 | 14-15 | 15-16 | 16-17
Planning
Planning Workflow | [51 empty] | Hardware | [8 empty] | Done
Producing Gantt Cart | [51 empty] | Software | [8 empty] | Done
Risk Assessment | [51 empty] | Everyone | [8 empty] | Done
Gantt Cart Review | [60 empty] | Done
Risk Assessment Review | [60 empty] | Done
Designing
Designing Initial Circuit | [60 empty] | Done
PIC Programming
Testing Interface | [60 empty] | Done
Building Testing Platform | [60 empty] | Done
Testing AR1010 | [60 empty] | Done
Research Programming Infos
Program AR1010 | [60 empty] | Done
Testing Radio Station | [60 empty] | Done
Program LCD | [60 empty] | Done
Testing LCD | [60 empty] | Done
Program Button | [60 empty] | Done
Checking Button | [60 empty] | Done
Finial Debugging | [60 empty] | Done
Breadboard (Testbed)
Building Power Regulator | [60 empty] | Done
Building Audio Ampuflier | [60 empty] | Done
Breadboarding Whole Circuit | [60 empty] | Done
Veroboard
Soldering PIC Wiring | [60 empty] | Done
Soldering Voltage Regalator | [60 empty] | Done
Soldering Audio Ampuflier | [60 empty] | Done
Testing Board | [60 empty] | Done
Final Design Testing
Testing Main Function | [60 empty] | Done
Testing Full Circuit | [60 empty] | Done
Design Box
Designing on Sketchup | [60 empty] | Done
3D Printing | [60 empty] | Done
Check Box | [60 empty] | Done
Assembly
Assemble PCB into Box | [60 empty] | Done
Final Test
Final Debugging | [60 empty] | Not Started
Presentation
Presentation

## Sheet2
Risk Assessment | Risks | Risk Level | Measurements
Planning | No real risks | Low | None
Designing | No real risks | Low | None
Programming | Dependant part of project / Might not compile | High | Increase programming debugging time
Breadboard | Use of wrong components | Low | Crosscheck
PIC Trainer | Use of wrong components / Error in soldering | Low | Crosscheck
Design PCB | Error in design (Wrong size or components) | High | Crosscheck
Final Design Testing | Missed error while testing | High | Crosscheck
Design Box | Error in design (Wrong size) | High | Crosscheck
Build PCB | Use of wrong components / Error in soldering | Medium | Crosscheck
Build Box | Manufacturing Issue | Medium
Assembly | Damage to Components | Medium
Final Test | Damage to Components | Low